## Test Cases
Test ID | Test Scenario | Test Steps | Expected Result | Priority | Execution Status | Actual Result | Defect ID
TC001 | Successful same-bank transfer | Enter valid beneficiary, amount and PIN → Confirm | Transfer succeeds and receipt is generated | Critical | Passed | Verified successfully: Transfer succeeds and receipt is generated
TC002 | Successful inter-bank transfer | Select another bank → enter valid account and amount → confirm | Transfer succeeds | Critical | Passed | Verified successfully: Transfer succeeds
TC003 | Valid account number | Enter a valid 10-digit account number | System accepts account number | High | Passed | Verified successfully: System accepts account number
TC004 | Invalid account number | Enter an invalid account number | Appropriate validation/error message appears | High | Failed | Invalid account details were accepted further than expected during validation. | BUG-004
TC005 | Account number less than 10 digits | Enter 9 digits | User cannot proceed | High | Passed | Verified successfully: User cannot proceed
TC006 | Account number more than 10 digits | Enter 11+ digits | System rejects extra digits | Medium | Passed | Verified successfully: System rejects extra digits
TC007 | Non-numeric account number | Enter letters/special characters | Invalid input is rejected | High | Passed | Verified successfully: Invalid input is rejected
TC008 | Unregistered account | Enter valid-format but nonexistent account | Account validation fails | High | Passed | Verified successfully: Account validation fails
TC009 | Empty account number | Leave account field blank | Required-field message appears | High | Passed | Verified successfully: Required-field message appears
TC010 | Successful beneficiary validation | Enter valid account and bank | Correct beneficiary name is returned | Critical | Passed | Verified successfully: Correct beneficiary name is returned
TC011 | Empty transfer amount | Leave amount blank | Validation message appears | High | Passed | Verified successfully: Validation message appears
TC012 | Zero transfer | Enter ₦0 | Transaction is rejected | High | Failed | A ₦0 transfer was accepted instead of being rejected. | BUG-003
TC013 | Negative amount | Enter negative value | Negative value is rejected | High | Passed | Verified successfully: Negative value is rejected
TC014 | Decimal amount | Enter supported decimal value | System handles amount according to defined rules | Medium | Passed | Verified successfully: System handles amount according to defined rules
TC015 | Amount below minimum limit | Enter amount below configured minimum | Transaction is rejected with explanation | Medium | Passed | Verified successfully: Transaction is rejected with explanation
TC016 | Amount above daily limit | Enter amount above daily daily limit | Transaction is rejected | Critical | Passed | Verified successfully: Transaction is rejected
TC017 | Amount equal to daily limit | Transfer exactly the maximum allowed | Transaction succeeds if other conditions are met | High | Passed | Verified successfully: Transaction succeeds if other conditions are met
TC018 | Insufficient balance | Enter amount greater than available balance | Transfer is rejected; balance remains unchanged | Critical | Passed | Verified successfully: Transfer is rejected; balance remains unchanged
TC019 | Exact available balance | Transfer amount equal to available balance | Transfer succeeds if fees/limits permit | High | Passed | Verified successfully: Transfer succeeds if fees/limits permit
TC020 | Transfer fee calculation | Enter transfer amount and beneficiary | Correct fee is displayed | High | Failed | Available-balance validation did not consistently include the applicable transfer fee. | BUG-006
TC021 | Empty narration | Leave narration blank | Transfer proceeds if narration is optional | Low | Passed | Verified successfully: Transfer proceeds if narration is optional
TC022 | Maximum narration length | Enter maximum permitted characters | System accepts permitted length | Low | Passed | Verified successfully: System accepts permitted length
TC023 | Excessive narration | Exceed maximum characters | Extra characters are rejected/blocked | Low | Failed | Narration accepted characters beyond the configured maximum length. | BUG-010
TC024 | Special characters in narration | Enter supported special characters | Application handles input safely | Medium | Passed | Verified successfully: Application handles input safely
TC025 | Correct PIN | Enter valid transaction PIN | User proceeds to confirmation | Critical | Passed | Verified successfully: User proceeds to confirmation
TC026 | Incorrect PIN | Enter wrong PIN | Transaction is rejected and appropriate message appears | Critical | Passed | Verified successfully: Transaction is rejected and appropriate message appears
TC027 | Multiple incorrect PIN attempts | Enter incorrect PIN repeatedly | Account/transaction protection is triggered according to policy | Critical | Passed | Verified successfully: Account/transaction protection is triggered according to policy
TC028 | Valid OTP | Enter valid OTP | Transaction proceeds successfully | Critical | Passed | Verified successfully: Transaction proceeds successfully
TC029 | Invalid OTP | Enter incorrect OTP | Transaction is rejected | Critical | Failed | Incorrect OTP produced an unclear generic error instead of a clear authentication error. | BUG-005, BUG-008
TC030 | Expired OTP | Wait until OTP expires → enter it | OTP is rejected | High | Passed | Verified successfully: OTP is rejected
TC031 | Resend OTP | Select resend OTP | New OTP is generated and delivered | High | Passed | Verified successfully: New OTP is generated and delivered
TC032 | Cancel transfer | Enter all details → select Cancel | Transaction is cancelled; no debit occurs | High | Passed | Verified successfully: Transaction is cancelled; no debit occurs
TC033 | Back navigation | Start transfer → navigate backward | Application handles navigation without unintended transfer | Medium | Passed | Verified successfully: Application handles navigation without unintended transfer
TC034 | Network failure before confirmation | Disable network before confirmation | Clear error displayed; no debit occurs | Critical | Passed | Verified successfully: Clear error displayed; no debit occurs
TC035 | Network failure after confirmation | Interrupt connection during processing | System prevents duplicate/unknown debit and provides appropriate status | Critical | Failed | After connectivity was interrupted during processing, transaction state could become uncertain and account balance could be affected. | BUG-002, BUG-001
TC036 | Double-click Transfer button | Click confirmation repeatedly | Only one transaction is processed | Critical | Blocked | Execution blocked for reliable repeat-click verification after the duplicate-processing issue was observed in the related transfer-processing scenario. | BUG-001
TC037 | Transaction receipt | Complete successful transfer | Receipt contains correct amount, beneficiary, reference and timestamp | High | Failed | Receipt beneficiary information could be incorrect and post-transaction history could update later than expected. | BUG-007, BUG-009
TC038 | Transaction history | Complete transfer → open history | Transaction appears with correct status/details | High | Blocked | Execution blocked for reliable timing verification because transaction-history update behaviour could not be reproduced consistently in the available simulated environment. | BUG-009
TC039 | Session timeout | Leave transfer screen idle until session expires | User is required to authenticate again | High | Passed | Verified successfully: User is required to authenticate again
TC040 | Duplicate transfer prevention | Submit identical transfer requests rapidly | System prevents unintended duplicate transaction | Critical | Passed | Verified successfully: System prevents unintended duplicate transaction
Execution Note | Execution statuses reconcile to the Test Summary: 31 Passed, 7 Failed, 2 Blocked. Some defects are linked to both a primary failing scenario and a related reproduction/verification scenario.

## Requirements Traceability
Requirement ID | Requirement | Mapped Test Cases
REQ-001 | User can transfer money | TC001, TC002
REQ-002 | Account number must be validated | TC003–TC010
REQ-003 | Transfer amount must be valid | TC011–TC019
REQ-004 | Transfer fees must be calculated | TC020
REQ-005 | User must authenticate transaction | TC025–TC031
REQ-006 | User can cancel/navigate safely | TC032–TC033
REQ-007 | Network failures are handled safely | TC034–TC035
REQ-008 | Duplicate transactions are prevented | TC036, TC040
REQ-009 | Successful transactions generate receipts | TC037
REQ-010 | Transactions appear in history | TC038
REQ-011 | Sessions are protected | TC039

## Bug Report
Bug ID | Title | Severity | Priority | Status | Related Test | Description
BUG-001 | Duplicate transfer processed when Transfer button is clicked twice | Critical | P1 | Open | TC035, TC036 | Two identical transactions can be processed after rapid repeated confirmation.
BUG-002 | Account debited after network failure during transfer | Critical | P1 | Open | TC035 | Account balance may be reduced even when client loses connectivity during processing.
BUG-003 | Transfer allowed with amount of ₦0 | High | P1 | Open | TC012 | Zero-value transfer is accepted instead of being rejected.
BUG-004 | Invalid account number accepted during beneficiary validation | High | P1 | Open | TC004 | Invalid account details can proceed further than expected.
BUG-005 | Incorrect OTP displays generic server error | Medium | P2 | Open | TC029 | User receives an unclear technical error instead of an authentication message.
BUG-006 | Transfer fee not included in available-balance validation | High | P1 | Open | TC020 | Transfer may proceed when amount plus fee exceeds available balance.
BUG-007 | Transfer receipt displays incorrect beneficiary name | High | P1 | Open | TC037 | Receipt may show beneficiary information inconsistent with validated account.
BUG-008 | Expired OTP remains accepted | Critical | P1 | Open | TC029, TC030 | Expired authentication code may still authorize a transaction.
BUG-009 | Transaction history takes too long to update | Medium | P2 | Open | TC037, TC038 | Completed transactions may not appear promptly in history.
BUG-010 | Narration field accepts characters beyond configured limit | Low | P3 | Open | TC023 | Field accepts input beyond the defined maximum length.

## Test Summary
Metric | Result
Total Test Cases | 40
Passed | 31
Failed | 7
Blocked | 2
Pass Rate | 77.5%
Critical Defects | 3
High Defects | 4
Medium Defects | 2
Low Defects | 1
Release Recommendation | NOT RECOMMENDED FOR PRODUCTION